## User Stories
Rank | User Story | Alternate Version or Notes | Order | Acceptance Criteria | Tests | Tasks | Task 1 Hours | Task 2 Hours | Task 3 Hours | Task 4 Hours | Task 5 hours | Task 6 Hours | Task Total Hours | Sprint | Feature | Feature Explanation | Sprint List | Sprint Total Hours | Sprint Possible Hours | Creating Tasks/AC
1 | As a developer I need to have a comprehensive style guide So that I can properly implement the UI |  |  | All portions of the application are wireframed, styles are accessible, major parts of the website are styled | All components and functionality are represented in the wireframes. All styles take accessibility into account. | 1) Create wireframe for all application pages, 2) Create styles for major website parts (buttons, logo, text, etc.), 3) Component structure outline | 4 | 4 | 4 |  |  |  | 12 | 1 | UI Guide | General UI style/design and consistency | Sprint 1 | 90 | 90
2 | As a working parent I want to quickly get reward recommendations So that I can spend less time shopping | Needs to be fleshed out in acceptance criteria - definition of quickly | Important | Get best card recommended within 5 seconds of accessing item or store profile, Reward recommendation is relevant to the store/item | Create user account, input credit and loyalty cards, visit store while signed in, check recommended card is best available in inputted cards for the store | 1) Set up Credit Card API key, 2) Set up API call to get updated Credit Card information as needed, 3) Set up component to hold top credit card recommendation, 4) Set up database to store User Information, 5) Create automated tests | 1 | 3 | 3 | 2 | 2 |  | 11 | 1 | Recommendation Engine | Recommendation engine credit card backend and user database setup | Sprint 2 | 90 | 90
3 | As a frequent traveler I want to get the best deals relative to my location So that I can save money on the go |  | Important | Accurate location data is found, Relevant deals at the current location found, API errors handled without crashing app | Create user account, sign in on mobile device, allow access to geolocation data, verify that deals are from stores around the present location of the phone. Set a different location manually, verify that deals are from stores present in the different location | 1) Set up Geolocation API key, 2) Set up Deals API key (Axesso is an option), 3) Set up Coupons API key, 4) Set up component for user to personally input location, 5) Set up button for user to manually enable automatic geolocation, 6) Add table to user database to store location history | 1 | 2 | 1 | 4 | 1 | 1 | 10 | 1 | Recommendation Engine | Recommendation engine geolocation backend and user database setup | Sprint 3 | 67 | 67
4 | As a loyalty and credit cards holder I want to register for an account So that I can manage and optimize my card usage |  | Important | Account is secure, Passwords are encrypted | Create a user account, add a credit card to the account, verify that the user data is stored in the correct database | 1) Add table to user database for storing user login information, 2) Add table to user database for information from initial survey, 3) Set up backend logic for creating a new user, 4) Set up component to capture user information from survey, 5) Set up component to capture user information from registration including existing cards if possible, 6) Create automated tests | 1 | 1 | 3 | 4 | 4 | 2 | 15 | 1 | Account Creation | User database/backend setup for accounts and credit cards |  | 247
5 | As a registered user I want to be able to access my account so that I can manage my saved information |  | Important | Account UI is accessible for logged in users, takes user to correct account page, non-registered users are sent to a signup form, account information can be edited, account can be deleted, wallet can be accessed | Account UI is accessible for logged in users, takes user to correct account page, non-registered users are sent to a signup form, account information can be edited, account can be deleted, wallet can be accessed | 1) Create account UI component, 2) backend logic to pull/edit user data, 3) delete account functionality, 4) Create automated tests | 7 | 2 | 1 | 2 |  |  | 12 | 1 | Account Creation | Account UI and creation/deletion functionality |  |  |  | JK
6 | As a regular credit/loyalty card user I want to be able to add new credit/loyalty cards to my account So that I can manage my rewards easier |  | Important | Credit/loyalty cards are added to wallet/database for future use | Create a user account, go to the user profile, select the UI element to add credit cards and add a credit card and a loyalty card to the account. Verify that the credit card and loyalty card were added to the right table in the database | 1) Set up component to take in details about credit/loyalty cards, 2) Connecting credit/loyalty card details to existing user database table, 3) Create automated tests | 5 | 2 | 2 |  |  |  | 9 | 1 | Account Creation | Credit card and loyalty card storage system
7 | As an independent student I want to find the best coupons So that I can save money for rent | As an avid consumer | Important | User can access coupons specific to them, coupons are relevant, coupons are valid, functionality to copy coupon code, API errors are handled without crashing app | User can access coupons specific to them, coupons are relevant, coupons are valid, functionality to copy coupon code, API errors are handled without crashing app | 1) Coupon component, 2) backend logic to send/receive API info, 3) Create automated tests | 5 | 3 | 2 |  |  |  | 10 | 1 | Recommendation Engine | Recommendation engine coupon backend |  |  |  | JK
8 | As a busy consumer I want to authenticate myself So that I can see optimized deals and history | As a consumer I want to authenticate myself So that I can see optimized deals and history for me | Important | User can successfully login after entering the correct information, a user cannot login to an account with incorrect info, a user cannot login with no info entered, error messages appear if user has entered incorrect info, there is a place for users to register for an account, users are taken to a new page after successful login | User can successfully login after entering the correct information, a user cannot login to an account with incorrect info, a user cannot login with no info entered, error messages appear if user has entered incorrect info, there is a place for users to register for an account, users are taken to a new page after successful login | 1) Create login component, 2) backend logic to compare entered information to DB info, 3) create landing page for where user will be redirected to after success, 4) create error handling for incorrect user info, 5) create way for user to register if no account, 6) Create automated tests | 5 | 2 | 4 | 2 | 2 | 2 | 17 | 2 | Account Creation | Account creation authentication functionality |  |  |  | JK
9 | As a forgetful user I want to be able to retrieve a lost password So that I can maintain access to my account |  | Important | user must be able to successfully reset password, on completetion the password is changed in the DB, user must be verified by code sent to email, email code must be verfieid by backend, code should expire after an hour | user must be able to successfully reset password, on completetion the password is changed in the DB, user must be verified by code sent to email, email code must be verfieid by backend, code should expire after an hour | 1) Create forgot password component, 2) backend logic to verify email address to an existing account, 3) backend logic to generate one time code to authenticate the user with the correct email, 4) backend logic to verify entered code, 5) backend logic to reset password, 6) Create automated tests | 6 | 1 | 3 | 1 | 1 | 2 | 14 | 2 | Account Creation | Account modification functionality |  |  |  | JK
10 | As a cautious customer I want the application to be secure so that my data does not get leaked/stolen |  | Important | A user can enter their information into the application knowing that it will be securely encrypted in the database. | Ensure database records are encrypted, API calls return encrypted data, and that data related to the logged-in user is only returned. | 1) Implement encryption at rest, 2) encryption in transit, and 3) client-side encryption when accessing data. 4) Ensure that API calls return data related only to the user by adding backend logic to verify user is only accessing their data. 5) Create automated tests | 2 | 2 | 1 | 1 | 2 |  | 8 | 1 | System Integrity | Record encryption and security |  |  |  | DE
11 | As a destitute customer I want the application to be free/cheap, so that I can access the application. |  | Important | A user must be able to create an account and access coupon deals free of charge. | Ensure that the login, sign up and home pages have no cost barrier. | 1) Ensure that their are no UI/UX and cost barriers or challenges to accessing site or creating an account. | 3 | [5 empty] | 3 | 1 | System Integrity | Account encryption and security |  |  |  | DE
12 | As a disgruntled user I want to be able to delete my account So that I can remove my information from the service |  | Important-Mid-Important | A user must be able to click the delete account button and confirm that deleting account would permanently delete all user data. Upon confirming, all user data must be deleted from the database. User can no longer log in. | Ensure that all data related to the user that is deleting account is permanently removed from the database. | 1) Add backend logic that removes user data from user table. 2) Cascade delete user data - remove records from other tables that reference specified user ID as foreign key. 3) In the user profile, add a delete button option along with a warning message upon click. After account is deleted, redirect to home or login page. 4) Create automated tests | 2 | 2 | 2 | 2 |  |  | 8 | 2 | Account Creation | Account deletion functionality |  |  |  | DE
13 | As a shopper with a list I want to search for items So that I can find deals for items to buy beforehand |  | Mid-Important | User must be able to enter an item name in the search bar and upon hitting enter, a list is populated with deals/coupons relevant to the searched item. | Ensure that deals/coupons related to the searched item are returned. | 1) Create a page/view with a search bar UI component and list UI component that list deals for items searched. 2) Invoke a call to Coupon/Deals API with the searched text as a query parameter. 3) Populate results into list component. 4) Create automated tests | 4 | 1 | 3 | 2 |  |  | 10 | 2 | System Integrity | Search engine functionality |  |  |  | DE
14 | As a customer I want to click through an item link to the corresponding web store So that I can purchase the item |  | Mid-Important | A feature exists such that users are able to click on an item through our application and be redirected instantly to the corresponding website and item in that store | Ensure items are clickable and redirect to the appropriate page | 1) Set up UI component representative of item linked to relevant website, 2) Create backend logic to grab website using Coupons/Deals API, 3) Create automated tests | 3 | 1 | 2 |  |  |  | 6 | 2 | Routing/Navigation | Item redirection |  |  |  | RR
15 | As a fiscally responsible user I want to be able to track rewards usage for specific cards So that I can best manage my rewards |  | Mid-Important | A feature exists such that users can input and track reward usage for a specific card, with confirmations to ensure purchases happened. A UI exists such that users can view their reward usage/history with information such as date, card, and reward type | Ensure users can log in, enter reward usage for specific cards, and then be delivered the relevant history | 1) Create database element to store list of rewards used for each specific card, 2) Create backend logic to save relevant information like card/reward type/amount spent, 3) Create UI component for users to view their reward usage history, 4) Create automated tests | 1 | 1 | 6 |  |  |  | 8 | 2 | User Mangement | Credit/loyalty card logging history |  |  |  | RR
16 | As a patient customer I want to be able to save searched items So that I can track the deals and price for that item |  | Mid-Important | A feature exists such that users can "favorite" or save searched items, and they can then access/view these searched items through a UI component | Ensure that users can log in, save specificly searched items, and then be delivered the relevant saved items | 1) Create database element to store each user's searched items, 2) Create backend logic to save information such as item searched and deals/price of item, 3) Create UI component for users to view saved items | 1 | 2 | 2 | 5 |  |  | 10 | 2 | User Mangement | Favoriting/saving system for items |  |  |  | RR
17 | As a mobile user I want to be able to access reward recommendations via smartphone So that I can search for deals while shopping in-store |  | Mid-Important | A UI exists such that it fits to the specification of a mobile screen, easily navigable, and easily readable, allowing users to see their reward recommendations | Using an Android/iOS device, test each feature present in our application to ensure a mobile-friendly experience, and adjust accordingly | 1) Ensure UI components are mobile-friendly, making it easy for users to access recommendations and applicaiton features through their smartphone, 2) Create automated tests | 3 | 2 |  |  |  |  | 5 | 3 | Routing/Navigation | UI enhancement/modification for mobile |  |  |  | RR
18 | As a busy consumer I want to be informed when products are on sale So that I am motivated to purchase them |  | Mid-Important |  | Set up a dummy item in the backend with currently active sale. Sign in as a user and open the homepage. Select the dummy item and favorite/track it. Change the dummy item's price in the backend. If the user gets an email about the item, then the test passes | 1) Add component to allow to select stores/items to follow, 2) Add table to user information database to contain tracked stores/items, 3) Set up custom email notification system, 4) Create automated tests | 3 | 1 | 3 | 2 |  |  | 9 | 2 | Recommendation Engine | Sales backend and notifications |  |  |  | JP
19 | As a regular shopper I want to be able to see deals from my favorite stores So that I can find items that I may be interested in |  | Mid-Less-Important |  | Set up a user account, answer the user survey, select at least one favorite store in the survey or later in the user profile. Open the homepage while signed in as that new user. The user should see a section on the homepage that displays deals from their favorited store(s) | 1) Add component to user profile to display deals from favorite stores, 2) Create automated tests | 3 | 2 |  |  |  |  | 5 | 3 | User Mangement | Favoriting system for stores |  |  |  | JP
20 | As a frequent shopper I want my shopping history to be saved So that I can return to a shopping session |  | Mid-Less Important |  | Sign into a user account. Search for several items using search functionality, close the webpage. Reopen the web app and check the user profile for the previously searched for items. The test passes if the previous searches were logged | 1) Add table to user information table for search/shopping history, 2) Implement backend logic to log search/shopping history, 3) add component to user profile to display search/shopping history, 4) Create automated tests | 1 | 2 | 3 | 2 |  |  | 8 | 2 | User Mangement | Shopping history backend and database |  |  |  | JP
21 | As an unregistered user I want to see general deals for popular stores So that I can make informed shopping decisions |  | Mid-Less Important |  | Open the web application in a non-signed in state. The homepage should contain deals from popular stores/websites | 1) Set up component to display deals on the homepage for an unregistered user, 2) Create automated tests | 4 | 2 |  |  |  |  | 6 | 3 | User Mangement | Guest user functionality for popular store deals |  |  |  | JP
22 | As an unregistered user I want to see coupons for popular stores So that I can save money in potential purchases |  | Mid-Less Important | Homepage for the app should have a component populated with coupons from popular stores. | Open the web application in a non-signed in state. The homepage should contain coupons from popular stores/websites. | 1) Set up a component to display the coupons to the user. 2) Create automated tests | 5 | 2 |  |  |  |  | 7 | 3 | User Mangement | Guest user functionality for popular store coupons |  |  |  | Anurag
23 | As an unregistered user I want to be able to see the best possible credit or loyalty card for a shopping location So that I can gather information about which cards to apply for |  | Mid-Less Important | For an unregistered user searching a shopping location in the search bar should populate a component on UI with best credit or loyalty card along with a show more button. Clicking on show more button further populates the component with upto next ten top cards suitable for user. | Open the web application in a non-signed state. Ensure that search input form takes the user input accurately. Ensure that clicking on search button provides a best card option to the user. Ensure that show more button below the best card option displays more options for card to the user. | 1) Set up a component to get search input from user for a shopping location. 2) Implement logic to sort the API result based on user's input. 3) Set up a component to display the best card to the user. 4) Set up a component to display next ten top cards extracted from applying the logic. 5) Create automated tests | 6 | 2 | 2 | 4 | 2 |  | 16 | 3 | Recommendation Engine | Guest user functionality for credit/loyalty cards |  |  |  | Anurag
24 | As a consumer I want reward recommendations and deals to be up to date So that I can acquire correct and accurate information |  | Less-Important | User is able to login successfully. Home screen of logged in user should have a component displaying recommendations and deals along with a expired button for user to report expired deals. | Ensure that user can login to his profile. Ensure that deals are populated on the home screen. Ensure that expired button fuctions correctly to record and submit the expired deals in the database. | 1) Retrieve deals and rewards. 2) Display deals to the user. 3) Implement a expired button for the user to report expired deals and rewards. 4) Store the expired deals and rewards in the database in order to filter them out in next API call. 5) Create automated tests | 1 | 4 | 1 | 1 | 2 |  | 9 | 3 | System Integrity | Report item functionality |  |  |  | Anurag
25 | As a web-application user I want to be able to seamlessly navigate through the app So that I don’t think twice about what to do next |  | Less-Important | A UI that is easy to operate and navigate, allowing the user to access functionailty quicky. Positive user feedback. Ensure all interfaces are consistent | Perform Alpha and Beta testing and perform a user experience survey. | 1) Ensure that user interfaces is consistent. 2) Reduce cognitive load and make it comfortable to interact with a application (i.e., remove irrelevant or rarely used elements), 3) Create automated tests | 2 | 2 |  |  |  |  | 4 | 3 | Routing/Navigation | Navigation and UI enhancements |  |  |  | Ayush
26 | As a discerning customer I want to see popular items separated by category on the home page So that I can find items in the right category to buy | As a discerning customer I want to see popular items separated by category of my favorite categories on the home page So that I can find items in the right category to buy | Less-Important | Most used coupons used in that store displayed to the user. Coupons related to user marked favourite items displayed to the user. | Sign in to the user account. Coupons related to selected user item displayed on the screen. 2. Select a store. Most popular coupons of that store displayed on the screen. | 1. Create a new user profile. Select and mark several items as favourite. 2. Call coupon API to retrieve most popular coupons from the selected store and display the items on the screen. 3. Create automated tests | 3 | 2 | 2 |  |  |  | 7 | 3 | Recommendation Engine | Coupon deliverance functionality |  |  |  | Ayush
27 | As a confused customer I want to have a support portal So that my questions can be answered |  | Less-Important | Help/FAQ portal available on user profile and on the front application | Open the application. Help/FAQ link should be displayed on the front screen. Login to a user account. Help/FAQ link should be displayed on the user profile. | 1. Create a webpage with potential user related queries. 2. Link the webpage on the front screen of application and the user profile. Save and reload the application. 3. Create automated tests | 5 | 1 | 2 |  |  |  | 8 | 3 | System Integrity | Support portal |  |  |  | Ayush
| As an avid consumer I want to be able to view my credit/loyalty card recommendation on another shopping website using a browser extension So that I can make the best decision in context |  |  |  |  | 1) Create a manifest file, 2) Create backend logic to link Credit/Loyalty Card recommendation, 3) Create html page to display credit/loyalty card recommendation, 4) Set up developer accounts for browsers, 5) Publish the extension to the web stores for extensions | 1 | [7 empty] | #REF!
| As an avid consumer I want to be able to view my coupon recommendation on another shopping website using a browser extension So that I can make the best decision in context |  |  |  |  | 1) Create backend logic to link coupon recommendation, 2) Update html page to display coupon card recommendation, 3) Publish the extension
As an avid consumer I want to be able to view the price history of an item on another shopping website using a browser extension So that I can make the best decision in context
| As an avid consumer I want to be able to view my rewards usage on another shopping website using a browser extension So that I can make the best decision in context |  |  |  |  | 1) Create backend logic to link rewards usage, 2) Create html page to display rewards usage, 3) Publish the extension
As an fiscally responsible user I want to be able to track my purchases So that I can budget more easily
As an forward-thinking user I want to be able to plan future purchases So that I can make the best use of my money
[13 empty] | 247 | [7 empty] | Goal: 246

## Burndown Chart
| Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3
247 | 217 | 187 | 157 | 127 | 97 | 67 | 44.6667 | 22.3333 | 0

## Product Roadmap
Features |  | Sprint | Rank | Task Total Hours
UI Guide | General UI style/design and consistency | 1 | 1 | 12
Recommendation Engine | Recommendation engine credit card backend and user database setup | 1 | 2 | 11
| Recommendation engine geolocation backend and user database setup | 1 | 3 | 10
| Recommendation engine coupon backend | 1 | 7 | 10
| Sales backend and notifications | 2 | 18 | 9
| Guest user functionality for credit/loyalty cards | 3 | 23 | 16
| Coupon deliverance functionality | 3 | 26 | 7
Account Creation | User database/backend setup for accounts and credit cards | 1 | 4 | 15
| Account UI and creation/deletion functionality | 1 | 5 | 12
| Credit card and loyalty card storage system | 1 | 6 | 9
| Account creation authentication functionality | 2 | 8 | 17
| Account modification functionality | 2 | 9 | 14
| Account deletion functionality | 2 | 12 | 8
System Integrity | Record encryption and security | 1 | 10 | 8
| Account encryption and security | 1 | 11 | 3
| Search engine functionality | 2 | 13 | 10
| Report item functionality | 3 | 24 | 9
| Support portal | 3 | 27 | 8
Routing/Navigation | Item redirection | 2 | 14 | 6
| UI enhancement/modification for mobile | 3 | 17 | 5
| Navigation and UI enhancements | 3 | 25 | 4
User Management | Credit/loyalty card logging history | 2 | 15 | 8
| Favoriting/saving system for items | 2 | 16 | 10
| Favoriting system for stores | 3 | 19 | 5
| Shopping history backend and database | 2 | 20 | 8
| Guest user functionality for popular store deals | 3 | 21 | 6
| Guest user functionality for popular store coupons | 3 | 22 | 7
Week Duration | Hours
1 | 5 or less
2 | 10 - 6 |  | ROADMAP
3 | 11+ |  |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3
|  |  | Feature Categories | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
|  |  | UI Guide | Sprint 1 Week 1: General UI style/design and consistency
|  |  | Recommendation Engine | Sprint 1 Week 1: Recommendation engine credit card backend and user database setup
Recommendation engine geolocation backend and user database setup
Recommendation engine coupon backend
Sales backend and notifications
Coupon deliverance functionality
Guest user functionality for credit/loyalty cards
|  |  | Account Creation | Sprint 1 Week 1: User database/backend setup for accounts and credit cards
Account UI and creation/deletion functionality
Credit card and loyalty card storage system
Account creation authentication functionality
Account modification functionality
Account deletion functionality
|  |  | System Integrity | Sprint 1 Week 1: Record encryption and security
Account encryption and security
Search engine functionality
Report item functionality
Support portal
|  |  | Routing / Navigation | Sprint 2 Week 5: Item redirection
UI enhancement/modification for mobile
Navigation and UI enhancements
|  |  | User Management | Sprint 2 Week 4: Credit/loyalty card logging history
Favoriting/saving system for items
Shopping history backend and database
Guest user functionality for popular store deals
Guest user functionality for popular store coupons
Favoriting system for stores