## Sheet1
Features |  | Sprint | Rank | Task Total Hours
UI Guide | General UI style/design and consistency | 1 | 1 | 12
Recommendation Engine | Recommendation engine credit card backend and user database setup | 1 | 2 | 11
| Recommendation engine geolocation backend and user database setup | 1 | 3 | 10
| Recommendation engine coupon backend | 1 | 7 | 10
| Sales backend and notifications | 2 | 18 | 9
| Guest user functionality for credit/loyalty cards | 3 | 23 | 16
| Coupon deliverance functionality | 3 | 26 | 7
Account Creation | User database/backend setup for accounts and credit cards | 1 | 4 | 15
| Account UI and creation/deletion functionality | 1 | 5 | 12
| Credit card and loyalty card storage system | 1 | 6 | 9
| Account creation authentication functionality | 2 | 8 | 17
| Account modification functionality | 2 | 9 | 14
| Account deletion functionality | 2 | 12 | 8
System Integrity | Record encryption and security | 1 | 10 | 8
| Account encryption and security | 1 | 11 | 3
| Search engine functionality | 2 | 13 | 10
| Report item functionality | 3 | 24 | 9
| Support portal | 3 | 27 | 8
Routing/Navigation | Item redirection | 2 | 14 | 6
| UI enhancement/modification for mobile | 3 | 17 | 5
| Navigation and UI enhancements | 3 | 25 | 4
User Management | Credit/loyalty card logging history | 2 | 15 | 8
| Favoriting/saving system for items | 2 | 16 | 10
| Favoriting system for stores | 3 | 19 | 5
| Shopping history backend and database | 2 | 20 | 8
| Guest user functionality for popular store deals | 3 | 21 | 6
| Guest user functionality for popular store coupons | 3 | 22 | 7
Week Duration | Hours
1 | 5 or less
2 | 10 - 6 |  | ROADMAP
3 | 11+ |  |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3
|  |  | Feature Categories | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
|  |  | UI Guide | Sprint 1 Week 1: General UI style/design and consistency
|  |  | Recommendation Engine | Sprint 1 Week 1: Recommendation engine credit card backend and user database setup
Recommendation engine geolocation backend and user database setup
Recommendation engine coupon backend
Sales backend and notifications
Coupon deliverance functionality
Guest user functionality for credit/loyalty cards
|  |  | Account Creation | Sprint 1 Week 1: User database/backend setup for accounts and credit cards
Account UI and creation/deletion functionality
Credit card and loyalty card storage system
Account creation authentication functionality
Account modification functionality
Account deletion functionality
|  |  | System Integrity | Sprint 1 Week 1: Record encryption and security
Account encryption and security
Search engine functionality
Report item functionality
Support portal
|  |  | Routing / Navigation | Sprint 2 Week 5: Item redirection
UI enhancement/modification for mobile
Navigation and UI enhancements
|  |  | User Management | Sprint 2 Week 4: Credit/loyalty card logging history
Favoriting/saving system for items
Shopping history backend and database
Guest user functionality for popular store deals
Guest user functionality for popular store coupons
Favoriting system for stores